## Gantt Chart
Team Project Gantt Chart
Rural Planning and Economic Development ¦ PLAC 5500-001 / LPPP 5559-001 ¦ Fall 2026
Enter tasks, owners, dependencies, and dates. The weekly bars update from planned start and finish dates.
Team / project
Community / client
Version date | 2026-09-03
WBS | Phase | Task / decision | Deliverable / output | Owner | Support | Dependency | Planned start | Planned finish | Status | % complete | Client review? | Risk / blocker | Next action / note | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16
1.1 | Team setup | Complete team agreement | Signed team agreement |  |  |  | 2026-09-09 | 2026-09-16 | Not started | 0% | No
1.2 | Team setup | Confirm client agreement and review process | Client agreement |  |  | 1.1 | 2026-09-09 | 2026-09-18 | Not started | 0% | Yes
2.1 | 20% | Inventory and synthesize existing documents | Source synthesis |  |  |  | 2026-09-09 | 2026-09-20 | Not started | 0% | Yes
2.2 | 20% | Complete source-aware SWOT | SWOT diagnosis |  |  | 2.1 | 2026-09-14 | 2026-09-21 | Not started | 0% | Yes
2.3 | 20% | Establish visual system and early place reading | Design direction and early evidence |  |  |  | 2026-09-14 | 2026-09-22 | Not started | 0% | No
2.4 | 20% | Assemble Work Plan submission | Work Plan, 20% |  |  | 2.1, 2.2, 2.3 | 2026-09-19 | 2026-09-23 | Not started | 0% | No
3.1 | 40% | Draft working introduction | Working introduction |  |  | 2.4 | 2026-09-23 | 2026-10-03 | Not started | 0% | Yes
3.2 | 40% | Build document architecture | Design and document skeleton |  |  | 2.4 | 2026-09-23 | 2026-10-03 | Not started | 0% | Yes
3.3 | 40% | Assemble evidence and diagnosis | Maps, tables, observations, draft graphics |  |  | 2.1 | 2026-09-23 | 2026-10-06 | Not started | 0% | Yes
3.4 | 40% | Assemble 40% submission | Working Introduction and Document Architecture |  |  | 3.1, 3.2, 3.3 | 2026-10-03 | 2026-10-07 | Not started | 0% | No
4.1 | 60% | Draft substantive text and technical content | Substantive draft sections |  |  | 3.4 | 2026-10-07 | 2026-10-17 | Not started | 0% | Yes
4.2 | 60% | Develop alternatives and tradeoffs | Alternatives comparison |  |  | 3.3 | 2026-10-07 | 2026-10-18 | Not started | 0% | Yes
4.3 | 60% | Complete appropriate economic or feasibility screen | Transparent analysis |  |  | 3.3 | 2026-10-07 | 2026-10-18 | Not started | 0% | Yes
4.4 | 60% | Assemble first substantive draft | First Substantive Draft, 60% |  |  | 4.1, 4.2, 4.3 | 2026-10-17 | 2026-10-21 | Not started | 0% | No
5.1 | 80% | Place final-draft text and graphics | Integrated draft |  |  | 4.4 | 2026-10-21 | 2026-11-05 | Not started | 0% | Yes
5.2 | 80% | Complete recommendations and implementation path | Action and implementation content |  |  | 4.4 | 2026-10-21 | 2026-11-06 | Not started | 0% | Yes
5.3 | 80% | Run second-person technical and accessibility review | QA record |  |  | 5.1, 5.2 | 2026-11-04 | 2026-11-09 | Not started | 0% | No
5.4 | 80% | Assemble staff review draft | Staff Review Draft, 80% |  |  | 5.1, 5.2, 5.3 | 2026-11-07 | 2026-11-11 | Not started | 0% | Yes
6.1 | Final | Resolve authorized review comments | Comment-response matrix |  |  | 5.4 | 2026-11-11 | 2026-11-25 | Not started | 0% | Yes
6.2 | Final | Complete final quality, source, and accessibility checks | Final QA record |  |  | 6.1 | 2026-11-23 | 2026-12-04 | Not started | 0% | No
6.3 | Final | Package final product and editable source files | Final handoff package |  |  | 6.1, 6.2 | 2026-11-25 | 2026-12-08 | Not started | 0% | Yes
6.4 | Final | Deliver final product | Final Product, 100% |  |  | 6.3 | 2026-12-07 | 2026-12-09 | Not started | 0% | No
6.5 | Final | Prepare and deliver final presentation | Final Presentation |  |  | 6.3 | 2026-12-02 | 2026-12-09 | Not started | 0% | No
X.1 | [8 empty] | Not started | 0 | No
X.2 | [8 empty] | Not started | 0 | No
X.3 | [8 empty] | Not started | 0 | No
X.4 | [8 empty] | Not started | 0 | No
X.5 | [8 empty] | Not started | 0 | No
X.6 | [8 empty] | Not started | 0 | No
X.7 | [8 empty] | Not started | 0 | No
X.8 | [8 empty] | Not started | 0 | No
X.9 | [8 empty] | Not started | 0 | No
X.10 | [8 empty] | Not started | 0 | No
X.11 | [8 empty] | Not started | 0 | No
X.12 | [8 empty] | Not started | 0 | No
X.13 | [8 empty] | Not started | 0 | No
X.14 | [8 empty] | Not started | 0 | No
X.15 | [8 empty] | Not started | 0 | No
X.16 | [8 empty] | Not started | 0 | No
X.17 | [8 empty] | Not started | 0 | No

## Course Milestones
Course Milestones
Rural Planning and Economic Development ¦ PLAC 5500-001 / LPPP 5559-001 ¦ Fall 2026
These are the controlling course dates from the 2026-09-03 syllabus.
Milestone | Deadline | Weight | Submission rule
Team Agreement and Partner Work Plan | 2026-09-16 15:30 | Supports Work Plan | Due at start of class
Work Plan, 20% of Total Project | 2026-09-23 12:00 | 5% | One team member uploads to Canvas
Working Introduction and Document Architecture, 40% | 2026-10-07 12:00 | 10% | One team member uploads to Canvas
First Substantive Draft, 60% | 2026-10-21 12:00 | 10% | One team member uploads to Canvas
Staff Review Draft, 80% | 2026-11-11 12:00 | 10% | One team member uploads to Canvas
Final Product, 100% | 2026-12-09 12:00 | 15% | One team member uploads to Canvas
Final Presentation | 2026-12-09 15:30 | 5% | Team presentation